## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | Yes | Auto Scheduled | Requirement Specification | 12 days | May 14, 2019 8:00 AM | May 29, 2019 5:00 PM |  | 1
2 | Yes | Auto Scheduled | Survey Volunteerer | 1 wk | May 14, 2019 8:00 AM | May 20, 2019 5:00 PM |  | 2
3 | Yes | Auto Scheduled | Questionare Organization | 1 wk | May 14, 2019 8:00 AM | May 20, 2019 5:00 PM |  | 2
4 | Yes | Auto Scheduled | Define Problem Statement of Volunteer & Organiztion | 3 days | May 21, 2019 8:00 AM | May 23, 2019 5:00 PM | 2,3 | 2
5 | Yes | Auto Scheduled | Business Analysis for System | 2 days | May 24, 2019 8:00 AM | May 27, 2019 5:00 PM | 4 | 2
6 | Yes | Auto Scheduled | Create System Specification | 2 days | May 28, 2019 8:00 AM | May 29, 2019 5:00 PM | 5 | 2
7 | Yes | Auto Scheduled | System Architecture Design | 15 days | May 30, 2019 8:00 AM | June 19, 2019 5:00 PM | 1 | 1
8 | Yes | Auto Scheduled | Design Database for multi usage | 1 day | May 30, 2019 8:00 AM | May 30, 2019 5:00 PM | 6 | 2
9 | Yes | Auto Scheduled | Design Web API for manipulate | 1 day | May 31, 2019 8:00 AM | May 31, 2019 5:00 PM | 8 | 2
10 | Yes | Auto Scheduled | Design Web App for Administrator | 3 days | June 3, 2019 8:00 AM | June 5, 2019 5:00 PM | 9 | 2
11 | Yes | Auto Scheduled | Design Mobile App Mockup for Volunteer & Organization | 2 wks | June 6, 2019 8:00 AM | June 19, 2019 5:00 PM | 10 | 2
12 | Yes | Auto Scheduled | Implementation | 14.38 days? | June 20, 2019 8:00 AM | July 10, 2019 11:00 AM | 7 | 1
13 | Yes | Auto Scheduled | Generate DB first .NET framework | 2 hrs | June 20, 2019 8:00 AM | June 20, 2019 10:00 AM | 8 | 2
14 | Yes | Auto Scheduled | Export API from Database manipulate | 1 hr | June 20, 2019 10:00 AM | June 20, 2019 11:00 AM | 13 | 2
15 | Yes | Auto Scheduled | Create frontend Web VueJS for Administrator | 6 days | June 20, 2019 11:00 AM | June 28, 2019 11:00 AM | 14 | 2
16 | Yes | Auto Scheduled | Scaffolding project from template | 1 day | June 20, 2019 11:00 AM | June 21, 2019 11:00 AM | 9 | 3
17 | Yes | Auto Scheduled | Authenticating and token handler | 1 day | June 21, 2019 11:00 AM | June 24, 2019 11:00 AM | 16 | 3
18 | Yes | Auto Scheduled | Implementing dashboard page | 1 day | June 24, 2019 11:00 AM | June 25, 2019 11:00 AM | 17 | 3
19 | Yes | Auto Scheduled | Implementing CRUD system entities | 1 day | June 25, 2019 11:00 AM | June 26, 2019 11:00 AM | 18 | 3
20 | Yes | Auto Scheduled | Implementing configuration | 1 day | June 26, 2019 11:00 AM | June 27, 2019 11:00 AM | 19 | 3
21 | Yes | Auto Scheduled | Attach API to template | 1 day | June 27, 2019 11:00 AM | June 28, 2019 11:00 AM | 20 | 3
22 | Yes | Auto Scheduled | Apply CI/CD for Web Admin | 2 hrs | June 20, 2019 8:00 AM | June 20, 2019 10:00 AM |  | 2
23 | Yes | Auto Scheduled | Create Mobile App | 8 days? | June 28, 2019 11:00 AM | July 10, 2019 11:00 AM | 10 | 2
24 | Yes | Auto Scheduled | Scaffolding project from template | 1 day? | June 28, 2019 11:00 AM | July 1, 2019 11:00 AM | 21 | 3
25 | Yes | Auto Scheduled | Login and register screen | 1 day? | July 1, 2019 11:00 AM | July 2, 2019 11:00 AM | 24 | 3
26 | Yes | Auto Scheduled | Authenticating and token handler | 1 day? | July 2, 2019 11:00 AM | July 3, 2019 11:00 AM | 25 | 3
27 | Yes | Auto Scheduled | Implementing home screen | 1 day? | July 3, 2019 11:00 AM | July 4, 2019 11:00 AM | 26 | 3
28 | Yes | Auto Scheduled | Implement events/organizations page | 1 day? | July 4, 2019 11:00 AM | July 5, 2019 11:00 AM | 27 | 3
29 | Yes | Auto Scheduled | Implement news, post, update, delete events | 1 day? | July 5, 2019 11:00 AM | July 8, 2019 11:00 AM | 28 | 3
30 | Yes | Auto Scheduled | Implement organization management | 1 day? | July 8, 2019 11:00 AM | July 9, 2019 11:00 AM | 29 | 3
31 | Yes | Auto Scheduled | Attach API to application | 1 day? | July 9, 2019 11:00 AM | July 10, 2019 11:00 AM | 30 | 3
32 | Yes | Auto Scheduled | Validation | 2 days | July 10, 2019 11:00 AM | July 12, 2019 11:00 AM | 12 | 1
33 | Yes | Auto Scheduled | QC for Web | 2 days | July 10, 2019 11:00 AM | July 12, 2019 11:00 AM | 14 | 2
34 | Yes | Auto Scheduled | QC for Mobile | 2 days | July 10, 2019 11:00 AM | July 12, 2019 11:00 AM | 23 | 2

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
1 | Phan Tran Hoang Duong | D | Work |  |  |  |  | 100% | 180,000 ₫/h | 0
2 | Nguyen Thi Ha Anh | A | Work |  |  |  |  | 100% | 120,000 ₫/h | 0
3 | Vu Minh Duy | V | Work |  |  |  |  | 100% | 120,000 ₫/h | 0
4 | Nguyen Hong Phat | P | Work |  |  |  |  | 100% | 150,000 ₫/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Survey Volunteerer | Nguyen Thi Ha Anh | 1 | 40h | 100%
Questionare Organization | Vu Minh Duy | 1 | 40h | 100%
Define Problem Statement of Volunteer & Organiztion | Phan Tran Hoang Duong | 0.33000000000000002 | 24h | 100%
Business Analysis for System | Phan Tran Hoang Duong | 0 | 16h | 100%
Create System Specification | Vu Minh Duy | 0 | 16h | 100%
Design Database for multi usage | Nguyen Thi Ha Anh | 0 | 8h | 100%
Design Web API for manipulate | Nguyen Hong Phat | 0 | 8h | 100%
Design Web App for Administrator | Vu Minh Duy | 0 | 24h | 100%
Design Mobile App Mockup for Volunteer & Organization | Phan Tran Hoang Duong | 0 | 80h | 100%
Generate DB first .NET framework | Phan Tran Hoang Duong | 0 | 2h | 100%
Export API from Database manipulate | Vu Minh Duy | 0 | 1h | 100%
Scaffolding project from template | Vu Minh Duy | 0 | 8h | 100%
Authenticating and token handler | Nguyen Hong Phat | 0 | 8h | 100%
Implementing dashboard page | Nguyen Hong Phat | 0 | 8h | 100%
Implementing CRUD system entities | Phan Tran Hoang Duong | 0 | 8h | 100%
Implementing configuration | Nguyen Thi Ha Anh | 0 | 8h | 100%
Attach API to template | Nguyen Hong Phat | 0 | 8h | 100%
Apply CI/CD for Web Admin | Phan Tran Hoang Duong | 0 | 2h | 100%
Scaffolding project from template | Nguyen Hong Phat | 0 | 8h | 100%
Login and register screen | Nguyen Thi Ha Anh | 0 | 8h | 100%
Authenticating and token handler | Phan Tran Hoang Duong | 0 | 8h | 100%
Implementing home screen | Vu Minh Duy | 0 | 8h | 100%
Implement events/organizations page | Nguyen Hong Phat | 0 | 8h | 100%
Implement news, post, update, delete events | Nguyen Thi Ha Anh | 0 | 8h | 100%
Implement organization management | Nguyen Hong Phat | 0 | 8h | 100%
Attach API to application | Vu Minh Duy | 0 | 8h | 100%
QC for Web | Phan Tran Hoang Duong | 0 | 16h | 100%
QC for Mobile | Nguyen Thi Ha Anh | 0 | 16h | 100%