## Sheet1
Created by |  | PhatNH |  |  | Date:22/07/2019
No. | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Status
1 | 2 | Requirement is not clear | The requirement for the system given by the user (volunteer & organization leader) can be vague and misunderstanding. | 1 | Not taking properly survey before starting the project. The questionnaire may have a problem that causes the answer wrong from expectation | Volunteers fill the form. Organizations answer the interview | Developer Team can build the prototype for getting feedback. BA and PM should gain more experience in requirement gathering. Meeting should be held between stakeholder as soon as possible | Bussiness Analysis Project Manager | 30% | Can lead the system to the wrong destination. Can not be implemented | Solved
2 | 3 | So few Organization & Volunteer using system. | The user join in the system very little so the data for further function cannot be established. | 2 | The marketing strategy does not affect | Organizations don't want to submit a registration form. The volunteers give up using the app | Give more reward for using the system. Have a better marketing strategy |  | 35% | The shortage of volunteer can lead to the drop out of an organization. The shortage of event from an organization can cause to the interest of volunteer | Unsolved
3 | 2 | System architect of Volunteer API Server does not have an authentication layer. | The volunteer can use the function of an organization. | 6 | Developer team can forget to implement the authentication layer. The Business Analysis can have the mistake when design the system architect | The volunteer tries to call the organization function | Re-design the system architect with the addition of the authentication layer. Re-implementation the API layer with authentication services | Developer Team Business Analysis | 10% | Crash the system when the request call from the volunteer missing the parameter for services. The information will be vague in the database if the request call is a success | Solved
4 | 3 | So many users on the system make the system overloading. | The number of users in one specific time can be huge, make the system have a problem when trying to response each request. | 2 | This could happen due to the careless of the developer team when implementing the system. Or this even can be happened because of hosting site, the virtual cloud that team have rent | In the evening, when the user and organization leader have need to use the system to post and retrieve information about upcoming event | Optimizing the system, add more filtering to divide requests into specific controller to downside the request at container at once. Rent the premium pack of cloud virtual machine | Developer Team Budget Manager | 10% | The system will slowdown which is an impact on user experience. The user will not want to use the system anymore | Unsolved
5 | 3 | The deliverables are not released on time. | The system schedule to serve the community before summer because it has time for both volunteers and organization to make an event. But, the system release after summer. | 3 | The project manager controls the schedule and team progress badly | The developer team late their deadline and project manager can control it. | More milestone should be established to make the developer team follow | Developer Team Project Manager | 15% | The system finishes after summer end, no one needs the system | Unsolved
6 | 4 | The search engine of the system does not satisfy user need. | The search engine does not provide the volunteer what organization or event that near them, make them difficult to join in or support community. | 1 | The Business Analysis not analyze accurately the search requirement. The Developer Team implement wrong the given design | When the user want to search for an upcoming event near them and the system recognized his nearest event is 100km | BA redesign the search engine that provides the accuracy. Developer team re-implement the search engine | Developer Team Business Analysis | 20% | The most significant function which connects the volunteer and organization event could not be used to make the system useless | Solved
7 | 2 | Lack of Overall Budget | Every activity in project team need budget. No money make it pending | 4 | The provided budget from the beginning is not enough. In developed time, some activities could drain off money for another | Salary for a human resource not enough | Searching for another angel investor. Establish the suitable plan for project timeline | Project Manager Budget Manager | 30% | The project will pending until having the money or it can stop forever | Solved
Risk categories |  |  |  | Risk Rank
1 | Business Risk |  |  | 1 | Extremely important
2 | Operational Risk |  |  | 2 | Important
3 | Schedule Risk |  |  | 3 | Normal
4 | Budget Risk |  |  | 4 | Minor
5 | Quality and Process Risk
6 | Technical Risk
Roles in project
1 | Project manager
2 | Technical leader
3 | Developer
4 | Tester
5 | Quality Assurance